## Slide 1
2019
Literature Survey
Implement Base Game
Level Generation
Gameplay
Report
Sep 2019
Oct
Nov
Dec
100
Sep 29 - Oct 4
Literature Search
100%
Oct 5 - Oct 25
Literature Survey
0%
Sep 29 - Oct 31
Build base FPS features
0%
Nov 1 - Dec 1
Prototype level generation
0%
Nov 1 - Dec 1
Prototype room decoration
Jan 2020
Feb
Mar
Level generator
Dec 3 - Mar 31
Room generator
Dec 3 - Mar 31
Add gameplay
Jan 1 - Mar 31
Progress report
Sep 29 - Dec 13
Final report
Sep 29 - Mar 31

## Slide 2
2019
Literature Survey
Implement Base Game
Level Generation
Gameplay
Report
Sep
Oct
Nov
Dec
100%
Sep 29 - Oct 4
Literature Search
100%
Oct 5 - Oct 25
Literature Survey
100%
Sep 29 - Oct 31
Build base FPS features
100%
Nov 1 - Dec 1
Prototype level generation
100%
Nov 1 - Dec 1
Prototype room decoration
2020
Feb
Mar
Level generator
Dec 3 - Mar 31
Room generator
Dec 3 - Mar 31
Add gameplay
Jan 1 - Mar 31
Progress report
Sep 29 - Dec 13
Final report
Sep 29 - Mar 31