## Sheet1
cards__name | cards__labels__name | Requirement type | Requirement | Priority | Status
Procedural re-generation of levels | Epic | Epic | Write Project Proposal | Should Have | Done
Progress Report | Epic | Requirement | Research PCG | Should Have | Done
Prototype Room Decoration | Epic | Requirement | Write proposal | Should Have | Done
Level Generator | Epic | Epic | Write Literature Review | Should Have | Done
Room Generator | Epic | Requirement | Research/find literature | Should Have | Done
Add Gameplay | Epic | Requirement | Get feedback | Should Have | Done
Final Report | Epic | Requirement | Write review | Should Have | Done
Decide PCG re-gen approach | Task | Epic | Build base FPS features | Must Have | Done
Implement PCG level re-generator | Story | Requirement | Create title/game over screens | Should Have | Done
Re-plan with new epic | Task | Requirement | Create end goal, transitions to end screens | Should Have | Done
Write Progress Report | Task | Requirement | Implement first person controller | Must Have | Done
Implement better decorations (remove sight lines between rooms) | Story | Epic | Prototype level generation | Must Have | Done
Implement room decoration filling algorithm | Story | Requirement | Design room tile prefabs | Must Have | Done
Design room decoration prefabs | Story | Requirement | Implement "random walk" generation | Must Have | Done
Critical path and filled tiles are slightly mis-aligned | Bug | Requirement | Implement maze filling algorithm | Must Have | Done
Prototype Level Generation | Epic | Requirement | Implement different sized tiles | Could Have
Implement maze filling algo (fills maze not on critical path) | Story | Epic | Prototype room decoration | Must Have | Done
Implement "random walk" generation (guaranteed path through maze) | Story | Requirement | Design room decoration prefabs | Must Have | Done
Design room tile prefabs | Story | Requirement | Implement room decoration filling algorithm | Must Have | Done
Build Base FPS Features | Epic | Requirement | Design random sub-decorator agents | Could Have | Done
Create end goal, transition to end screen | Story | Epic | Progress report | Must Have | Done
Create start/end screens | Story | Requirement | Design plan | Should Have | Done
Implement first person controller | Story | Requirement | Write first draft | Should Have | Done
|  | Requirement | Write final draft and submit | Must Have
|  | Epic | Prototype re-generation | Must Have
|  | Requirement | Design approach for re-generating parts of level in real-time | Must Have
|  | Requirement | Implement re-generation process | Must Have
|  | Requirement | Implement re-generation trigger process | Must Have
Critical path breaks (needs down exit but is blocked) when left bound reached | Bug | Epic | Level generator | Must Have
|  | Epic | Room generator | Must Have
|  | Epic | Level re-generator | Must Have
|  | Epic | Basic gameplay | Must Have
|  | Epic | Enhanced gameplay | Should Have
|  | Epic | Final report | Must Have